## 工作表1
“A+ for 8” Group Meeting
Meeting Date | Meeting Time | Meeting Venue | Meeting Minutes
4/10/2023 | 1:00pm | Online | 60
Attendees:
Attendees | Attended | Regret | Notes
Yantong Chen | ●
Junxiang Wang |  | ●
Kunlun Huang | ●
Wenkai Kong | ●
Xi Chen | ●
Xiaoxuan Wang | ●
Yinglin Zheng | ●
Jun Wang | ●
Agenda:
Meeting Agendas
1. Progress updates on individual work tasks.
2. Refinement of software requirements.
3. Submission deadline for requirement forms(2023/10/08, 23:59).
4. Determination of initial architecture.
Personal Summary
Yantong Chen | Confirmed and consolidated the software requirements and documented them in a comprehensive document.
Wenkai Kong | Implemented a basic backend framework using Flask and SQLite.
Xi Chen | Comfirmed The frontend requirements and the frontend framework to be used were determined.
Yinglin Zheng
Kunlun Huang
Xiaoxuan Wang | Ran a partial code testing program and uploaded it to GitHub
Jun Wang
Software Architecture
The software Architecture can be roughly decomposed into frontend and backend components. After further decomposition, the backend can be further classified into algorithm modules and logic modules. Additionally, the frontend can be roughly categorized into static code analysis and dynamic web page analysis modules.
Submission Deadline for Requirement Forms
All team members were reminded of the requirement to submit the completed requirement forms by the agreed deadline of October 8, 2023. This deadline allows sufficient time for review and consolidation of the requirements.
Next Meeting Time： | 18/10/2023 2:00pm